## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
1 | FS 1 / Req_1 and 2 | Login | In this admin or user will login with its credentials. | Task #1 | Create the login form jsp so that admin or user can enter details and redirection to respective homepage. | Critical | Nimit | 28/3/19 | 28/3/19 | 6 | M | Completed | The objective of this requirement is to allow the admin or user to login and redirect to respective home page. | Admin or User being able to access the homepage & get redirected to the ‘Login’ page upon click of ‘Login’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task #2 | Create LoginController LoginDao, LoginDAOImpl, LoginService, LoginServiceImpl Layer in Spring MVC to Save and Validate the Data. | Critical | Nimit | 28/3/19 | 29/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #3 | Login Validation using database , spring security and redirect to Home Page | Critical | Nimit | 29/3/19 | 29/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task #4 | Integration All | Medium | Nimit | 29/3/19 | 29/3/19 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
2 | FS 2 / Req_3 and 4 | Book Management by Admin | As an admin, I want to land on Admin Home page which will display choices of adding or removing book. | Task#1 | Create a jsp page for Admin Home and successfully land on it after validating credentials. | High | Mohit | 29/3/19 | 30/3/19 | 6 | M | Completed | The objective of this requirement is to allow the admin to add book or remove it from database. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Fetch all the books from the database by creating AddBook, BooksController | Critical | Amitoj | 29/3/19 | 30/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | Create a 'Add Book' and redirect to Add Book Page and submit the details in the database. | Critical | Amitoj | 31/03/19 | 31/03/19 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#4 | View or remove the book details by fetching it from the database using the bookName and displaying it on a new page. | High | Amitoj | 31/03/19 | 2019-01-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#6 | Integrate the code and verify its working. | Critical | Amitoj | 2019-03-04 | 2019-04-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  | User Registration | As an user, I want to open user registration page and save the entered user details. | Task#1 | Create a registeration JSP page to accept the data from user as per the field of user table. | Critical | Mohit | 2019-05-04 | 2019-06-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Create UserRegistration,UserDAo, UserController, UserService class to insert the user data and controller and verify on backend. | Critical | Nimit | 2019-06-04 | 2019-06-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | Integrate the code and verify its working . | Medium | Nimit | 2019-06-04 | 2019-06-04 | 6 | S | Completed |  |  | Scrum Master | Average | High | New Requirement
3 | FS 2 / Req_5 and 6 | User Home | As an user, I want to land on User Home page which will display all the books from the database | Task#1 | Create a jsp page for User Home and successfully land on it after validating credentials. | Low | Mohit | 2019-06-04 | 2019-08-04 | 6 | S | Completed | The objective of this requirement is to allow the user to select and add book to the cart. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Fetch all the books from the database. |  | Amitoj | 2019-08-04 | 2019-09-04 | 6 | M | Completed | The objective of this requirement is to allow the user to login and redirect to user home page. | user being able to access the homepage & get redirected to the ‘Admin HomePage’ page upon click of 'login’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | View the book details by fetching it from the database using the bookName and displaying it on a new page |  | Nimit |  |  | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
3 |  | Book Payment | As an user, I want to buy the book and make payment via different payment methods and update the status from pending to paid | Task#4 | By clicking on the 'Checkout' one should be redirected to payment page which has options on it. |  | Monika | 2019-10-04 | 2019-10-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#5 | Create a jsp page with payment options |  | Monika | 2019-10-04 | 2019-10-04 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
|  |  |  | Task#6 | After redirecting and selecting a valid payment method, Payment Details Page would be loaded |  | Monika | 2019-10-04 | 2019-11-04 | 6 | M | Completed | The objective of this requirement is to allow the user to add book for purchasal and pay via required method. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#7 | Create a checkout, payment and controller |  | Amitoj | 2019-11-04 | 2019-11-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#9 | Enter the valid Card number and CVV number and update in the database |  | Amitoj | 2019-11-04 | 2019-11-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#10 | After successful payment message is generated for order status. |  | Monika | 2019-12-04 | 13/4/2019 | 6 | S | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#11 | Integrate the code and verify its working. |  | Monika | 13/4/2019 | 14/4/2019 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement