## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | User Login | As an user, I want to open Login page for user and Authenticate valid user. | Task#1 | Create a Login JSP page to accept UserId and Password and allow to login and provide with registration link to create account. | High | Mohit | 28/3/19 | 28/3/19 |  |  | Done
|  |  |  | Task#2 | Create a jsp page and redirect to User Registration Page. | High | Mohit | 28/3/19 | 28/3/19 |  |  | Done
|  |  |  | Task#3 | Submit the data and store it in the database. | High | Nimit | 28/3/19 | 29/3/19 |  |  | Done
|  |  |  | Task#4 | Create User Entity class, User DAO and User Service class to insert the user data and controller and verify on backend. | High | Nimit | 29/3/19 | 29/3/19 |  |  | Done
|  |  |  | Task#5 | Successful login. | High | Nimit | 29/3/19 | 30/3/19 |  |  | Done
| #1 | User Registration | As an user, I want to open user registration page and save the entered user details. | Task#6 | Create a registeration JSP page to accept the data from user as per the field of user table. | High | Mohit | 30/3/19 | 30/3/19 |  |  | Done
|  |  |  | Task#7 | Create User Entity class, User DAO and User Service class to insert the user data and controller and verify on backend. | High | Nimit | 30/3/19 | 31/3/19 |  |  | Done
|  |  |  | Task#8 | Integrate the code and verify its working . | High | Nimit | 31/3/19 | 31/3/19 |  |  | Done
| #2 | User Home Page | As an User, I want to land user home page which will display all the books available from the database. | Task#9 | Create a jsp page for User Home and successfully land on it after validating credentials. | High | Mohit | 31/3/19 | 31/3/19 | 5 |  | Done
|  |  |  | Task#10 | Fetch all the books available from the database. | High | Nimit | 31/3/19 | 2019-01-04 | 11 |  | Done
|  |  |  | Task#11 | View the book details by fetching it from the database using the bookName and displaying it on a new page. | Medium | Nimit | 2019-01-04 | 2019-01-04 | 1 |  | Done
|  |  |  | Task#12 | Create User Entity class, User DAO and User Service class to add the slected book to the cart. | High | Amitoj | 2019-01-04 | 2019-01-04 |  |  | Done
|  |  |  | Task#13 | Create a 'Add to Cart' and redirect to Cart Page. | High | Amitoj | 2019-01-04 | 2019-02-04 |  |  | Done
|  |  |  | Task#14 | Submit the data and store it in the database. | High | Amitoj | 2019-02-04 | 2019-02-04 | 3 |  | Done
| #2 | Cart Page | As an user, I want to land on cart page which will display all the selected books with their quantity and price from the database. | Task#15 | Create a jsp page for cart page and successfully land on it after adding books to cart. | High | Amitoj | 2019-02-04 | 2019-02-04 | 3 |  | Done
|  |  |  | Task#16 | Fetch all the added books from the database by creating Policy class, Policy DAO, Policy Service and controller. | High | Amitoj | 2019-02-04 | 2019-03-04 | 11 |  | Done
|  |  |  | Task#17 | View the quantity and price of added books and generate final amount. | High | Monika | 2019-03-04 | 2019-03-04 | 10 |  | Done
|  |  |  | Task#18 | Create a 'checkout' and redirect to Payment page. | High | Monika | 2019-03-04 | 2019-03-04 | 13 |  | Done
|  |  |  | Task#19 | Submit the data and store it in the database. | High | Monika | 2019-03-04 | 2019-04-04 | 2 |  | Done
| #2 | Payment Page | As an user, I want to open payment page and pay the amount for ordered books. | Task#20 | Create a payment JSP page to accept the data from user as per the field of user table. | High | Monika | 2019-04-04 | 2019-04-04 | 2 |  | Done
|  |  |  | Task#21 | Create User Entity class, User DAO and User Service class to insert the user data and controller and verify on backend. | High | Amitoj | 2019-04-04 | 2019-04-04 | 15 |  | Done
|  |  |  | Task#22 | Enter the valid Card number and CVV number and update in the database | High | Amitoj |  |  |  |  | Done
|  |  |  | Task#23 | After successful payment , order status is shown. | Medium | Amitoj |  |  |  |  | Done
|  |  |  | Task#24 | Submit the data and store it in the database. | High | Monika | 2019-04-04 | 2019-05-04 | 15 |  | Done
|  |  |  | Task#25 | Integrate the code and verify its working for successful order. | Medium | Monika | 2019-05-04 | 2019-05-04 |  |  | Done
| #3 | Admin Login | As an user, I want to open Login page for admin and Authenticate valid admin. | Task#26 | Create a Login JSP page to accept AdminId and Password and allow to login. | High | Mohit | 2019-06-04 | 2019-06-04 | 2 |  | Done
|  |  |  | Task#27 | Create a jsp page and redirect to Admin HomePage. | High | Mohit | 2019-06-04 | 2019-10-04 | 3 |  | Done
|  |  |  | Task#28 | Submit the data and store it in the database. | Medium | Nimit | 2019-10-04 | 2019-11-04 | 5 |  | Done
|  |  |  | Task#29 | Create User Entity class, User DAO and User Service class to insert the user data and controller and verify on backend. | High | Nimit | 2019-11-04 | 2019-12-04 |  |  | Done
|  |  |  | Task#30 | Successful login. | High | Nimit | 2019-11-04 | 2019-12-04 |  |  | Done
| #3 | Admin Home Page | As an admin, I want to add new book to the database or view the existing one and delete the unrequired one. | Task#31 | Create a jsp page with options to add/view/remove book. | High | Mohit | 13/4/2019 | 14/4/2019 | 2 |  | Done
|  |  |  | Task#32 |  | High | [5 empty] | Done
|  |  |  | Task#33 | Create a 'Add book ' and redirect to page to accept the data from user as per the field of user table to add new book. | High | Amitoj | 13/4/2019 | 14/4/2019 | 3 |  | Done
|  |  |  | Task#34 | Create a'view/remove' to view details of book or to delete any book. | High | Amitoj | 14/4/2019 | 15/4/2019 | 10 |  | Done
|  |  |  | Task#35 | Submit the data and store it in the database | Medium | Amitoj | 14/4/2019 | 15/4/2019 | 3 |  | Done
|  |  |  | Task#36 | Integrate the code and verify its working. | High | Nimit | 15/4/2019 | 16/4/2019 | 6 |  | Done